## Directions
User story writing directions | Possible bids | Value in hours | Possible User story States
Step 1: Features | A | 2 | On Hold
Receive features from your AP about what feature absolutely must be completed by the end of the sprint | 2 | 4 | Sprint Backlog
Review the features and evaluate if there are any other features you feel should be tackled during the sprint | 3 | 8 | In Progress
| 5 | 12 | Complete
Step 2: Stories | 8 | 16
Break the features apart into deliverable tasks | J | 40
write a user story for each one of those tasks | Q | 80
write a list of test cases for each of the user stories | K | OMGWTFBBQ
Bidding Directions
Step 1: Bidding
Each person evaluates how difficult the task is without bias from other members.
They will represent that difficulty by how long they estimate the task will take to complete.
Each team member will pick which of the possible bids best represents how difficult they evaluate the task to be
Step 2: Negotiation
The team must have a consensus on how difficult the task is
Each team member reveals what bid they decided upon on the previous step
If there is a differing of bids the team must discuss why the bids differ and must come to an agreement on the tasks value
Step 3: Allocation
After every user story has been bided and have had all their values agreed upon the user stories must be assigned owners.
Generally the owner of a task should be the person that bided the lowest on that task.
Once all of the tasks have been assigned owners tally up the total value of each persons tasks
If the distribution of tasks is not even rebalance the tasks owners until it is.

## Team info
Team Name
Corona
Team Members | Phone # | Email
Jonathan Caro
Mike Hatter | 646.812.3749 | tbf4tal@yahoo.com
Pablo Leon | 787.349.5971 | rahiri@gmail.com
Sam Mathis | 903.330.1905 | Reverseirony@hotmail.com
Xiaodong Weng | 347.759.9505
Wheel spins
First well
Second wheel
Third wheel

## S1 Allocation
Sprint 3 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Jonathan Caro | Mike Hatter | Pablo Leon | Sam Mathis | Xiaodong Weng | 0 | Agreed upon bid | Owner
As a designer, I want the enemies to animate |  | 8 | 12 | 12 | 12 |  |  | 8 | Jonathan Caro
As a designer, I want the levels to have background Images |  | 4 | 4 | 2 | 2 |  |  | 2 | Pablo Leon
As a designer, I want the levels to have different background music |  | 2 | 2 | 2 | 2 |  |  | 2 | Mike Hatter
As a designer, I want all actions to have a sound effect associated with them |  | 8 | 8 | 8 | 12 |  |  | 8 | Mike Hatter
As a wheel, I want the team to create a questionairre to be given to testers during the expo |  | 4 | 4 | 4 | 4 |  |  | 4 | Sam Mathis
As a designer, I want to readjust the levels to support game progression |  | 8 | 8 | 8 | 4 |  |  | 8 | Sam Mathis
As a developer, I want player one and player two to die independently of each other. |  | 4 | 8 | 4 | 4 |  |  | 4 | Pablo Leon
As a developer, I want the attract mode to function properly |  | 12 | 8 | 12 | 12 |  |  | 8 | Mike Hatter
As a developer, I want to fix the bounce movement |  | 4 | 4 | 4 | 4 |  |  | 4 | Sam Mathis
As a programmer, I want the save to save the player's health, score, and energy levels. |  | 8 | 2 | 12 | 4 |  |  | 4 | Mike Hatter
As a user, I want the hud to provide more information |  | 2 | 2 | 2 | 2 |  |  | 2 | Pablo Leon
As a user, I want to differentiate the save slots |  | 8 | 8 | 12 | 4 |  |  | 8 | Mike Hatter
As a user, I want to save my high scores |  | 8 | 4 | 4 | 12 |  |  | 4 | Pablo Leon
As a user, I want a screen that tells me how to play |  | 4 | 4 | 4 | 4 |  |  | 4 | Jonathan Caro
As a user, I want to navigate all menus with the gamepad |  | 2 | 2 | 2 | 2 |  |  | 2 | Sam Mathis
As an artist, I want the correct player assets |  | 8 | 8 | 8 | 4 |  |  | 8 | Jonathan Caro
As an artist, I want a tile set that fits with the theme of the game |  | 80 | 2 | 4 | 2 |  |  | 4 | Pablo Leon
As an artist, I want each of the spells to have their own particle effect. |  | 8 | 4 | 8 | 8 |  |  | 8 | Pablo Leon
As an artist, I want the final sister assets |  | 8 | 8 | 8 | 8 |  |  | 8 | Jonathan Caro
As a Producer, I want this to work on the arcade machines |  | 8 | 12 | 12 | 2 |  |  | 2 | Sam Mathis
As a producer, I want the game to be TRC compliant |  | 2 | 2 | 2 | 2 |  |  | 2 | Sam Mathis
As an artist, I want to differentiate player one and player two graphically |  | 2 | 8 | 4 | 2 |  |  | 4 | Sam Mathis
You must insert rows above this point when adding user stories
Totals
|  | Jonathan Caro | Mike Hatter | Pablo Leon | Sam Mathis | Xiaodong Weng | 0 | Totals
|  | 28 | 30 | 24 | 26 | 0 | 0 | 108
you must insert rows above this point when adding user stories | Priority | Test cases
As a designer, I want the enemies to animate
All enemies have a movement animation
All enemies have an attack animation
All enemies have a death animation
As a designer, I want the levels to have background Images
Each level has a background image displayed
As a designer, I want the levels to have different background music
Each level has a unique background song
As a designer, I want all actions to have a sound effect associated with them
Sound is played when a terrain tile is destroyed
Sound is played when a spell is created
Sound is played when the player takes damage
As a wheel, I want the team to create a questionairre to be given to testers during the expo
Questionairre printed out
Questionairre handed out to testers
Questions on questionairre relate to game
As a designer, I want to readjust the levels to support game progression
Smaller levels
Smaller gaps to jump
Easier accesability to switches
As a developer, I want player one and player two to die independently of each other.
Player 1 dies when health reaches 0, regardless of player 2's health
Player 2 dies when health reaches 0, regardless of player 1's health
As a developer, I want the attract mode to function properly
Attact mode displays a video of gameplay when user is inactive in menus
As a developer, I want to fix the bounce movement
The characters do not "twitch" while standing still / walking
As a programmer, I want the save to save the player's health, score, and energy levels.
Health of both players is saved along with game data
Score of both players is saved along with game data
Energy levels of all elements are saved along with game data
As a user, I want the hud to provide more information
Energy levels of selected element is displayed in the hud
Score is displayed for player 2
Amount of Tier 3 energy displayed
As a user, I want to differentiate the save slots
Number of players displayed along with slot numbers
Current level displayed along with the slot numbers
As a user, I want to save my high scores
High score can be saved upon losing the game
High score can be saved upon winning the game
High scored displayed correctly from the menu
As a user, I want a screen that tells me how to play
Keyboard controls displayed for both players
Gamepad controls displayed
As a user, I want to navigate all menus with the gamepad
Gamepad controls menu item selection
Gamepad can be used to exit all menus
As an artist, I want the correct player assets
Player has correct images and animations
As an artist, I want a tile set that fits with the theme of the game | High
Tileset used resembles a cave
As an artist, I want each of the spells to have their own particle effect. | High
Tier 1 spells have unique particles effects for each element
Tier 2 spells have unique particles effects for each element
Tier 3 spells have unique particles effects for each element
Combined spells have unique particle effects
As an artist, I want the final sister assets
Sister boss has a movement animation
Sister boss has an attack animation
Sister boss has a death animation
As an artist, I want to differentiate player one and player two graphically
Player 1 has a unique image
Player 2 has a unique image
As a Producer, I want this to work on the arcade machines
Controls work on arcade machine
Game runs on arcade machine
As a producer, I want the game to be TRC compliant
Game is TRC compliant