## Directions
User story writing directions | Possible bids | Value in hours | Possible User story States
Step 1: Features | A | 2 | On Hold
Receive features from your AP about what feature absolutely must be completed by the end of the sprint | 2 | 4 | Sprint Backlog
Review the features and evaluate if there are any other features you feel should be tackled during the sprint | 3 | 8 | In Progress
| 5 | 12 | Complete
Step 2: Stories | 8 | 16
Break the features apart into deliverable tasks | J | 40
write a user story for each one of those tasks | Q | 80
write a list of test cases for each of the user stories | K | OMGWTFBBQ
Bidding Directions
Step 1: Bidding
Each person evaluates how difficult the task is without bias from other members.
They will represent that difficulty by how long they estimate the task will take to complete.
Each team member will pick which of the possible bids best represents how difficult they evaluate the task to be
Step 2: Negotiation
The team must have a consensus on how difficult the task is
Each team member reveals what bid they decided upon on the previous step
If there is a differing of bids the team must discuss why the bids differ and must come to an agreement on the tasks value
Step 3: Allocation
After every user story has been bided and have had all their values agreed upon the user stories must be assigned owners.
Generally the owner of a task should be the person that bided the lowest on that task.
Once all of the tasks have been assigned owners tally up the total value of each persons tasks
If the distribution of tasks is not even rebalance the tasks owners until it is.

## Team info
Team Name
Corona
Team Members | Phone # | Email
Jonathon Caro
Mike Hatter | 646.812.3749 | tbf4tal@yahoo.com
Pablo Leon | 787.349.5971 | rahiri@gmail.com
Sam Mathis | 903.330.1905 | Reverseirony@hotmail.com
Wheel spins
First well
Second wheel
Third wheel

## S1 Allocation
Sprint 3 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Jonathon Caro | Mike Hatter | Pablo Leon | Sam Mathis | 0 | 0 | Agreed upon bid | Owner
As a designer, I want a final boss, decided by how quickly the player gets to the end.
As a designer, I want an attract mode that attracts people.
As a designer, I want spells to increase in power the more you use that type of spell
As a designer, I want the enemies to be effected differently based on their type and spell type
As a designer, I want the player to hit switches to progress through the level
As a developer, I want Lava terrain to hurt the player
As a developer, I want the Air Currents in the game that push the player around
As a developer, I want the enemy spawner to respawn enemies
As a developer, I want the game to be arcade machine compliant
As a developer, I want the particle engine to be complete
As a developer, I want the tier 1 fire spells done
As a developer, I want the tier 1 ice spells done
As a developer, I want the tier 1 wind spells done
As a developer, I want tier 2 spells to rely on energy picked up in the game
As a developer, I want water terrain to hurt the player and flood the level
As a programmer, I want to implement a scoring system based on time and destruction
As a user, I want a free-fire mode while using the game pad
As a user, I want multiple earth spells
As a user, I want multiple fire spells
As a user, I want multiple ice spells
As a user, I want multiple wind spells
As a user, I want my option configurations saved auto-magically
As a user, I want my spells to cancel out hostile spells
As a user, I want the camera to function properly when playing with two players.
As a user, I want the earth enemies to decide which player to attack when playing with two players.
As a user, I want the spells of different elements to interact with each other
As a user, I want the spells to have effects on the alternate terrain
As a user, I want the state of the terrain to be saved
As a user, I want to play different multiplayer game modes such as co-op and death-match
As a user, I want to transition between levels
As a user, I would like to have a HUD.
As an Everyman, I want the enemies to behave differently
As a developer, I want to implement a win/lose condition
You must insert rows above this point when adding user stories
Totals
|  | Jonathon Caro | Mike Hatter | Pablo Leon | Sam Mathis | 0 | 0 | Totals
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Stories | Priority | Test cases
As a user, I want the camera to function properly when playing with two players.
Players shouldn’t fall off the screen.
If player goes off screen, is brought back.
As a user, I want the earth enemies to decide which player to attack when playing with two players.
Earth Enemies decide which player to attack based on Distance.
As a user, I want to be able to play with a friend… no homo.
Two playable characters can be controlled independantly of each other.