## Directions
User story writing directions | Possible bids | Value in hours | Possible User story States
Step 1: Features | A | 2 | On Hold
Receive features from your AP about what feature absolutely must be completed by the end of the sprint | 2 | 4 | Sprint Backlog
Review the features and evaluate if there are any other features you feel should be tackled during the sprint | 3 | 8 | In Progress
| 5 | 12 | Complete
Step 2: Stories | 8 | 16
Break the features apart into deliverable tasks | J | 40
write a user story for each one of those tasks | Q | 80
write a list of test cases for each of the user stories | K | OMGWTFBBQ
Bidding Directions
Step 1: Bidding
Each person evaluates how difficult the task is without bias from other members.
They will represent that difficulty by how long they estimate the task will take to complete.
Each team member will pick which of the possible bids best represents how difficult they evaluate the task to be
Step 2: Negotiation
The team must have a consensus on how difficult the task is
Each team member reveals what bid they decided upon on the previous step
If there is a differing of bids the team must discuss why the bids differ and must come to an agreement on the tasks value
Step 3: Allocation
After every user story has been bided and have had all their values agreed upon the user stories must be assigned owners.
Generally the owner of a task should be the person that bided the lowest on that task.
Once all of the tasks have been assigned owners tally up the total value of each persons tasks
If the distribution of tasks is not even rebalance the tasks owners until it is.

## Team info
Team Name
Corona
Team Members | Phone # | Email
Jonathon Caro
Mike Hatter | 646.812.3749 | tbf4tal@yahoo.com
Pablo Leon | 787.349.5971 | rahiri@gmail.com
Sam Mathis | 903.330.1905 | Reverseirony@hotmail.com
Wheel spins
First well
Second wheel
Third wheel

## S1 Allocation
Sprint 3 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Jonathon Caro | Mike Hatter | Pablo Leon | Sam Mathis | 0 | 0 | Agreed upon bid | Owner
As a designer, I want a final boss, decided by how quickly the player gets to the end.
As a designer, I want an attract mode that attracts people.
As a designer, I want spells to increase in power the more you use that type of spell
As a designer, I want the enemies to be effected differently based on their type and spell type
As a designer, I want the player to hit switches to progress through the level
As a developer, I want Lava terrain to hurt the player
As a developer, I want the Air Currents in the game that push the player around
As a developer, I want the enemy spawner to respawn enemies
As a developer, I want the game to be arcade machine compliant
As a developer, I want the particle engine to be complete
As a developer, I want the tier 1 fire spells done
As a developer, I want the tier 1 ice spells done
As a developer, I want the tier 1 wind spells done
As a developer, I want tier 2 spells to rely on energy picked up in the game
As a developer, I want to implement a win/lose condition
As a developer, I want water terrain to hurt the player and flood the level
As a programmer, I want to implement a scoring system based on time and destruction
As a user, I want a free-fire mode while using the game pad
As a user, I want a mini-map to help me get around the level
As a user, I want multiple earth spells
As a user, I want multiple fire spells
As a user, I want multiple ice spells
As a user, I want multiple wind spells
As a user, I want my option configurations saved auto-magically
As a user, I want my spells to cancel out hostile spells
As a user, I want the camera to function properly when playing with two players.
As a user, I want the earth enemies to decide which player to attack when playing with two players.
As a user, I want the spells of different elements to interact with each other
As a user, I want the spells to have effects on the alternate terrain
As a user, I want the state of the terrain to be saved
As a user, I want to play different multiplayer game modes such as co-op and death-match
As a user, I want to transition between levels
As a user, I would like to have a HUD.
As an Everyman, I want the enemies to behave differently
You must insert rows above this point when adding user stories
Totals
|  | Jonathon Caro | Mike Hatter | Pablo Leon | Sam Mathis | 0 | 0 | Totals
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Stories | Priority | Test cases
As a designer, I want a final boss, decided by how quickly the player gets to the end.
Dr. Kage Vikarof renders and is able to be killed and damage player.
Jennifer renders and is able to be killed and damage player.
Either Dr. Kage Vikarof or Jennifer appears as final boss based off time.
As a designer, I want an attract mode that attracts people.
If no input from the player while at the menu, a separate attract mode becomes active
Once there is input, attract mode ends.
As a designer, I want spells to increase in power the more you use that type of spell
Spell experience is gained on collision with enemy and terrain
Spell types level up based on experience.
Power of the spells increases as level increases
As a designer, I want the enemies to be effected differently based on their type and spell type
Damage is dealt based on elemental affinities.
As a designer, I want the player to hit switches to progress through the level
Switches placed through the level.
Switches activated when collide with player.
Switches allow for progression in the level
As a developer, I want Lava terrain to hurt the player
Lava deals damage to the player when the player is immersed
As a developer, I want the Air Currents in the game that push the player around
Air currents propel the player in the direction of the air flow
As a developer, I want the enemy spawner to respawn enemies
When an enemy dies, they are respawned when the spawner becomes off screen
As a developer, I want the game to be arcade machine compliant
Game works with Arcade machine controls
No memory leaks or warning.
Game does not crash.
As a developer, I want the particle engine to be complete
Particles will be rendered correctly
Particles dissapear when spells are destroyed
As a developer, I want the tier 1 fire spells done
Damage over time is applied to enemies upon contact with a fire spell
As a developer, I want the tier 1 ice spells done
Enemies are slowed when hit by ice spells
As a developer, I want the tier 1 wind spells done
Enemies are pushed back in the direction they are hit when hit by wind spells.
As a developer, I want tier 2 spells to rely on energy picked up in the game
Energy is dropped when enemies are killed
Energy can be picked up and stored by the players
Energy is required and deducted when using tier 2 spells.
As a developer, I want to implement a win/lose condition
The player loses when they run out of health and lives
Player achieves victory when they defeat the final boss
As a developer, I want water terrain to hurt the player and flood the level
Water damages the player when they are submerged.
When water will flood the level to a predefined flood height
As a programmer, I want to implement a scoring system based on time and destruction
Player earns score for destroying terrain
Player earns score for destroying enemies
Player earns score based of time when they defeat the final boss
As a user, I want a free-fire mode while using the game pad
Player can activate/deactivate free-fire mode using the gamepad
Player can aim spells using the right thumbstick
As a user, I want a mini-map to help me get around the level
HUD displays a mini-map to display nearby areas.
HUD updates when tiles are destroyed to display current terrain.
As a user, I want multiple earth spells
Tier 2 earth spell creates earth pillar that can be jumped on.
Tier 3 earth spell creates giant hand that rises and grabs enemies, killing them.
Tier 2 spell takes earth energy to use
As a user, I want multiple fire spells
Tier 2 fire spell creates a lava flow that damages terrain and enemies. goes away after a fixed time.
Tier 3 fire spell clears screen and displays particles
Tier 2 spell takes fire energy to use.
As a user, I want multiple ice spells
Tier 2 ice spell creates giant ice shard that can be jumped on and damage enemies.
Tier 3 ice spell "freezes" all enemies on screen, as well as lava terrain and water terrain.
Tier 2 spell takes ice energy to use.
As a user, I want multiple wind spells
Tier 2 wind spell creates a tornado that can propel the player upward as well as damage the enemy and terrain
Tier 3 wind spell creates an "aura" around the player that protects him from damage for a fixed time and pushes back enemies.
Tier 2 spell takes ice energy to use.
As a user, I want my option configurations saved auto-magically
Menu options, including sound volumes, saved after game is exited.
Configurations are loaded when the game loads.
As a user, I want my spells to cancel out hostile spells
Spells can negate enemy spells
Particle effect created when spell is negate/destroyed
As a user, I want the camera to function properly when playing with two players.
Players don’t fall of the screen
If Players fall of screen, they are brought back on screen
As a user, I want the earth enemies to decide which player to attack when playing with two players.
Earth enemies will attack nearest player
As a user, I want the spells of different elements to interact with each other
Player 1's spells collide with Player 2's spells
Original spells are destroyed.
New spell created in place of the destroyed spells
As a user, I want the spells to have effects on the alternate terrain
Boulders stop air currents for a fixed time when they collide
Ice freezes water and lava for a fixed time when they collide.
As a user, I want the state of the terrain to be saved
When the game is saved, the terrain is saved along with the player information
Destroyed tiles are not loaded with the level.
As a user, I want to play different multiplayer game modes such as co-op and death-match
Player can select Co-op, and deathmatch multiplayer modes
Deathmatch functions properly, and players can win/lose
Co-op mode functions properly with both players able to control their respective characters
As a user, I want to transition between levels
Player can reach end of level and next level will be loaded
Player will be able to function within additional levels
As a user, I would like to have a HUD.
HUD is visible on the screen
HUD provides vital game information to the player
HUD updates as game information changes
As an Everyman, I want the enemies to behave differently
Enemy types have different states/"behaviors"
Enemy types attack the players differently
Enemy types have different priorities.