## Directions
User story writing directions | Possible bids | Value in hours | Possible User story States
Step 1: Features | A | 2 | On Hold
Receive features from your AP about what feature absolutely must be completed by the end of the sprint | 2 | 4 | Sprint Backlog
Review the features and evaluate if there are any other features you feel should be tackled during the sprint | 3 | 8 | In Progress
| 5 | 12 | Complete
Step 2: Stories | 8 | 16
Break the features apart into deliverable tasks | J | 40
write a user story for each one of those tasks | Q | 80
write a list of test cases for each of the user stories | K | OMGWTFBBQ
Bidding Directions
Step 1: Bidding
Each person evaluates how difficult the task is without bias from other members.
They will represent that difficulty by how long they estimate the task will take to complete.
Each team member will pick which of the possible bids best represents how difficult they evaluate the task to be
Step 2: Negotiation
The team must have a consensus on how difficult the task is
Each team member reveals what bid they decided upon on the previous step
If there is a differing of bids the team must discuss why the bids differ and must come to an agreement on the tasks value
Step 3: Allocation
After every user story has been bided and have had all their values agreed upon the user stories must be assigned owners.
Generally the owner of a task should be the person that bided the lowest on that task.
Once all of the tasks have been assigned owners tally up the total value of each persons tasks
If the distribution of tasks is not even rebalance the tasks owners until it is.

## Team info
Team Name
Corona
Team Members | Phone # | Email
Jonathon Caro
Mike Hatter | 646.812.3749 | tbf4tal@yahoo.com
Pablo Leon | 787.349.5971 | rahiri@gmail.com
Sam Mathis | 903.330.1905 | Reverseirony@hotmail.com
Wheel spins
First well
Second wheel
Third wheel

## S1 Allocation
Sprint 1 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Jonathon Caro | Mike Hatter | Pablo Leon | Sam Mathis | 0 | 0 | Agreed upon bid | Owner
As a designer I want all of the buttons to function clearly and properly. |  | 2 | 4 | 2 | 2 |  |  | 2 | Sam Mathis
As a designer I want to be able to create and edit animations. |  | 8 | 8 | 8 | 8 |  |  | 8 | Sam Mathis
As a designer I want to be able to create and edit different particle effects |  | 4 | 8 | 8 | 16 |  |  | 8 | Mike Hatter
As a designer I want to be able to easily create and edit game levels with the world editor |  | 16 | 40 | 12 | 16 |  |  | 16 | Pablo Leon
As a designer I want to be able to preview the particle effects before being implemented into the game |  | 2 | 2 | 2 | 2 |  |  | 2 | Mike Hatter
As a developer I want a Profiling system to optimize code |  | 4 | 4 | 4 | 4 |  |  | 4 | Jonathon Caro
As a developer I want a State Machine to change states based on needs |  | 4 | 4 | 4 | 4 |  |  | 4 | Jonathon Caro
As a developer I want an Event system to send data between objects. |  | 8 | 8 | 8 | 4 |  |  | 4 | Sam Mathis
As a developer I want the maps to save and load using relative paths |  | 4 | 2 | 2 | 8 |  |  | 2 | Pablo Leon
As a developer I want the particles to save and load using relative paths |  | 4 | 4 | 4 | 8 |  |  | 4 | Mike Hatter
As a developer I want to create an Object Hierarchy, and systems to support them |  | 12 | 8 | 12 | 4 |  |  | 12 | Sam Mathis
As a developer I want to sumbit an Art Request to insure my game looks good. |  | 2 | 4 | 4 | 4 |  |  | 2 | Jonathon Caro
As a programmer I want an In-Game engine to load in the animations |  | 8 | 8 | 8 | 8 |  |  | 8 | Jonathon Caro
As a programmer I want an In-Game engine to render the maps |  | 16 | 16 | 12 | 16 |  |  | 12 | Pablo Leon
As a programmer I want an In-Game system to load and render the particle effects |  | 12 | 8 | 8 | 12 |  |  | 8 | Mike Hatter
As a programmer I want the menu systems and interface to be easy to use and understand |  | 8 | 8 | 8 | 8 |  |  | 8 | Mike Hatter
As a programmer I want to save many animations to one file, and save and load using relative paths |  | 4 | 4 | 4 | 2 |  |  | 2 | Sam Mathis
As a user I want enemies in the game, that I can pwn |  | 8 | 40 | 12 | 12 |  |  | 12 | Jonathon Caro
As a user I want tiles to be able to be destroyed |  | 4 | 4 | 4 | 4 |  |  | 4 | Pablo Leon
As a user I want to be able to control my character |  | 12 | 12 | 12 | 12 |  |  | 12 | Sam Mathis
As a user I want to be able to save and load my game. |  | 16 | 16 | 16 | 16 |  |  | 16 | Mike Hatter
As a user I want to be able to use the first tier of spells |  | 16 | 40 | 16 | 40 |  |  | 16 | Jonathon Caro
As a user I want to see characters, objects, spells, and terrain collide |  | 4 | 8 | 8 | 2 |  |  | 4 | Pablo Leon
You must insert rows above this point when adding user stories
Totals
|  | Jonathon Caro | Mike Hatter | Pablo Leon | Sam Mathis | 0 | 0 | Totals
|  | 46 | 46 | 38 | 40 | 0 | 0 | 170
User Stories | Priority | Test cases
As a designer I want all of the buttons to function clearly and properly on the Animation Editor
Animation editors must use a tool strip and file menus.
All buttons and options of the animation editor must function.
As a designer I want to be able to create and edit animations. |  | Animation editors must at a minimum support having an Image rect, Collisions rect and anchor point in each frame.
Animation editors must contain a playback window that will allow you to see the animation play in real time using an anchor point
Animation editors must support manual editing of previously entered information (numeric up down for all the current info and properties)
Animation editors must support tying game events with entering or exiting of animation frames
As a designer I want to be able to create and edit different particle effects |  | Particle editors must support changing of a particles color, velocity, scale and rotation over time.
Particle editors must support emitting from within a determined range (rect, circle, line…)
Particle editors must have the ability to determine if an effect is looping or only plays once.
Particle editors must have an option to randomize effects, with a configurable option to select which properties to modify.
Particle editors must support setting an use of DX Render State blend modes.
As a designer I want to be able to easily create and edit game levels with the world editor
Tile editors must support freehand drawing of tiles (drawing by clicking and dragging)
Tile editors must have the ability to create a map of an arbitrary size (rectangular shaped using whole numbers)
Tile editors must have the ability to load in a custom tile set using any image (bmp or png) with tiles of any size (32x32, 8x8, 32x8)
Tile editors must support at least one of the following: Multiple graphical layers, Layers for object spawning, paint bucket style area fill, or stamp style area fill)
Tile editors must support tying game events with its supported collision types
Tile editors must support adding collision information onto the map in either Tile or dynamically drawn rect based collisions
As a designer I want to be able to preview the particle effects before being implemented into the game
Particle Editor must support a preview window
As a developer I want a Profiling system to optimize code
A debug tool must be created that will profile functions for the duration it takes them to execute.
The Code profiler must use a high resolution timer.
The code profiler must be able to profile multiple functions at once.
The code profiler must output to a file the highest lowest average and a list of all the times the function was profiled.
The data compiled from the run is presented to the user clearly
As a developer I want a State Machine to change states based on needs
The game must be able to set to hold and run the current game state and support changing from one game state to another.
As a developer I want an Event system to send data between objects.
The game must be able to demonstrate an event system
As a developer I want the maps to save and load using relative paths
When the tile editor loads a previously saved file it must load associated files automatically as well (maps load the tile sheet).
Tile editors must be able to function with relative paths. The tile editor should be able to be run from anywhere and the tile editor should be able to load a file from anywhere without problem.
Tile editors must save and load binary files that will later be loaded by the game
As a developer I want to create an Object Hierarchy, and systems to support them
The game must contain all core game objects with base functionality
The game must support collision between game objects (rect to rect collision at a minimum)
The game demonstrates the ability to handle multiple objects on screen
The game must have a system built to create and manage game objects
As a developer I want to sumbit an Art Request to insure my game looks good.
An asset request must be filled out and approved by both your AP and the art director
As a programmer I want an In-Game engine to load in the animations
Characters and objects have animated movement
As a programmer I want an In-Game engine to render the maps
Levels from the world editor are loaded in, and rendered
As a programmer I want an In-Game system to load and render the particle effects
Flyweight data is loaded in
Particles are rendered to the screen
As a programmer I want the menu systems and interface to be easy to use and understand
The game must have a fully functional standard menu system (main menu, options menu, pause menu, how to play screens)
The game must use a bitmap or other texture based system to display text to the screen. Bitmapped fonts must support kerning.
The interface is easy to understand and use
All pieces of the interface work
The game must be fully navigable using nothing but the keyboard
The game must be fully navigable using nothing but a gamepad/controller
As a programmer I want to save many animations to one file, and save and load using relative paths
When the animation editor loads a previously saved file it must load associated files automatically as well (animations load the sprite sheet).
Animation editors must be able to function with relative paths. The animation editor should be able to be run from anywhere and the animation editor should be able to load a file from anywhere without problem.
Animation editors must save and load binary files that will later be loaded by the game
Animation editors must save and load xml files that will used during the creation of assets (not loaded by the game)
Animation editors must have the ability to save multiple animations per save file
As a user I want enemies in the game, that I can pwn
Enemies are visible in the game and can move around
Enemies can be damaged / destroyed
Enemies can damage the player
As a user I want tiles to be able to be destroyed
The player doesn't collide with tiles after they've been destroyed
As a user I want to be able to control my character
Keyboard input moves the player
Gamepad input moves the player
As a user I want to be able to save and load my game.
The player can save their location, score, and if the game is in co-op mode
The player can load in their game data
Multiple (3) different games can be stored and loaded
As a user I want to be able to use the first tier of spells
Spells can be created
Spells can collide with the player, enemies, each other and terrain
As a user I want to see characters, objects, spells, and terrain collide
The Player collides with spells, enemies, terrain, and other objects
The Enemies collide with spells and terrain.
The Spells collide with the terrain, and other spells.