## Directions
User story writing directions | Possible bids | Value in hours | Possible User story States
Step 1: Features | A | 2 | On Hold
Receive features from your AP about what feature absolutely must be completed by the end of the sprint | 2 | 4 | Sprint Backlog
Review the features and evaluate if there are any other features you feel should be tackled during the sprint | 3 | 8 | In Progress
| 5 | 12 | Complete
Step 2: Stories | 8 | 16
Break the features apart into deliverable tasks | J | 40
write a user story for each one of those tasks | Q | 80
write a list of test cases for each of the user stories | K | OMGWTFBBQ
Bidding Directions
Step 1: Bidding
Each person evaluates how difficult the task is without bias from other members.
They will represent that difficulty by how long they estimate the task will take to complete.
Each team member will pick which of the possible bids best represents how difficult they evaluate the task to be
Step 2: Negotiation
The team must have a consensus on how difficult the task is
Each team member reveals what bid they decided upon on the previous step
If there is a differing of bids the team must discuss why the bids differ and must come to an agreement on the tasks value
Step 3: Allocation
After every user story has been bided and have had all their values agreed upon the user stories must be assigned owners.
Generally the owner of a task should be the person that bided the lowest on that task.
Once all of the tasks have been assigned owners tally up the total value of each persons tasks
If the distribution of tasks is not even rebalance the tasks owners until it is.

## Team info
Team Name
Corona
Team Members | Phone # | Email
Jonathan Caro
Mike Hatter | 646.812.3749 | tbf4tal@yahoo.com
Pablo Leon | 787.349.5971 | rahiri@gmail.com
Sam Mathis | 903.330.1905 | Reverseirony@hotmail.com
Xiaodong Weng | 347.759.9505
Wheel spins
First well
Second wheel
Third wheel

## S1 Allocation
Sprint 3 Allocation |  | Bids | [5 empty] | Finals
User Stories |  | Jonathan Caro | Mike Hatter | Pablo Leon | Sam Mathis | Xiaodong Weng | 0 | Agreed upon bid | Owner
As a designer, I want the enemies to animate
As a designer, I want the levels to have background Images
As a designer, I want the levels to have different background music
As a designer, I want all actions to have a sound effect associated with them
As a designer, I want the health and damage of the player and enemies to be balanced out
As a designer, I want to readjust the levels to be more player friendly
As a developer, I want player one and player two to die independently of each other.
As a developer, I want the attract mode to function properly
As a developer, I want to fix the bounce movement
As a programmer, I want the save to save the player's health, score, and energy levels.
As a user, I want the hud to provide more information
As a user, I want to differentiate the save slots
As a user, I want to save my high scores
As a user, I want a screen that tells me how to play
As a user, I want to navigate all menus with the gamepad
As an artist, I want the correct player assets
As an artist, I want a tile set that fits with the theme of the game
As an artist, I want each of the spells to have their own particle effect.
As an artist, I want the final sister assets
As a Producer, I want this to work on the arcade machines
As an artist, I want to differentiate player one and player two graphically
You must insert rows above this point when adding user stories
Totals
|  | Jonathan Caro | Mike Hatter | Pablo Leon | Sam Mathis | Xiaodong Weng | 0 | Totals
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Stories | Priority | Test cases
As a designer, I want the enemies to animate
As a designer, I want the levels to have background Images
As a designer, I want the levels to have different background music
As a designer, I want all actions to have a sound effect associated with them
As a designer, I want the health and damage of the player and enemies to be balanced out
As a designer, I want to readjust the levels to be more player friendly
As a developer, I want player one and player two to die independently of each other.
As a developer, I want the attract mode to function properly
As a developer, I want to fix the bounce movement
As a programmer, I want the save to save the player's health, score, and energy levels.
As a user, I want the hud to provide more information
As a user, I want to differentiate the save slots
As a user, I want to save my high scores
As a user, I want a screen that tells me how to play
As a user, I want to navigate all menus with the gamepad
As an artist, I want the correct player assets
As an artist, I want a tile set that fits with the theme of the game
As an artist, I want each of the spells to have their own particle effect.
As an artist, I want the final sister assets
As an artist, I want to differentiate player one and player two graphically
As a Producer, I want this to work on the arcade machines